## Sheet1
| Details | Duration | Remark
1 | General
| Learn and study the existing themes, codings | 3 | [11/05 Tiffany] If build the new website i/o continuing the old one, will it be faster? (CP) Rebuild the new website would indeed take longer time.
| Set up tabs, categories and preferences | 1
2 | Home Page
| Home Page basic | 1.5
| Slider at home page | 0.5
3 | Promotion
| Basic Development | 1.5
| Automatically generate coming soon picture for inactive promotion | 0.5 | [11/06 Tiffany] What we need is to ensure there are always 5 fixed pics show on the Homepage no matter if we have 2 or 5 promotion activities…, will there any easy way to do? ex: to cut the linkage, just let the picture without promotion activity “inactive”? Since to spend 1.5 days to generate coming soon picture is too long for us. Thank you. (CP) The feature to automatically replace the promotion with "Coming Soon" pic could take 1.5 day. Because it involves checking the status of a category and then general specific html. If we need to save the development time, you can choose to maintain the promotion image manually. It is easy to maintained but need a little knowledge on HTML.
| PDF for login users only | 0.5 | [11/06 Tiffany] Please refer to the attachment 1 the sample PDF that we will put in promotion (CP) In our understanding, we are setting up the system so that promotion pdf file copies can be stored and downloaded for a login user.
| Calculate active/inactive by start date/end date – We have not figured out a way to do this yet in NetSuite yet. Our current customers do this manually. |  | [11/05 Tiffany] We are ok this for now
| Show available qty | 2 | Standard NetSuite does not show location inventory separately at website. We suggested to use scheduled scripting to update a custom location inventory balance record and display it at the website. How many active items you will have for the website. The frequency of updating and hence the accuracy of the inventory balance will be impacted by the number of active items. [11/05 Tiffany] For the first step, we will start from around 3000s items, but the total will be 6000s for our on hand items now. By using the scripting, will we need to update manually or it will update automatically? (CP) We will develop a web services to update the custom fields which store the location balance and updated them automatically and periodically. There will be a time lag between the order committed and balance updated.
| Next Available Date | 2 | Similarly, we need to develop scheduled scripting to update a next available date for every active website item which is stock out. Same constraint applies here as above. [11/06 Tiffany] Noted, please refer to the attached entry screen in where the information (Next Available Date) stored in Netsuite
4 | NEWS
| Basic Development | 1
| Automatically remove inactive news |  | We have not figured out a way to do this yet in NetSuite yet. Our current customers do this manually. [11/05 Tiffany] We are ok this for now
5 | Quick Order | 3 | [11/05 Tiffany] We don’t want our customer to see the Netsuite page, though we need to link to website page i/o Customer Portal (CP) I attached a screen capture which incorporate the customer center in eCommerce site. The NetSuite page can be quite subtle and share similar styling with the site. It will be much easier to tailor the quick entry form under this way and put in information like "Qty available" and "Next Available date" as the NetSuite shopping cart is not built for these types of functions and difficult to be customized. I estimated 3 days for Quick Order if we do it this way.
6 | Download
| Basic Development | 0.5
| Preview online feature | 1 | Language depending on the language of user computer – not achievable. Netsuite only remember the language preference of registered customer. We can provide a click button for user to change the language. [11/05 Tiffany] We only need the language-English, though it should be no problem
7 | Online Catalog
| Image Zoom in and Out | 1
| Basic Development | 2.5
8 | New Dealer Application | 1
9 | Contact Us
| Basic Development | 0.5
| Image Upload |  | [11/06 Tiffany] I think we could remove this function, thank you.
8 | Quotation | 0 | Remove this function
9 | Testing and Training | 3 | send somebody to our Hong Kong office after our development for testing and training. We estimate that will last 6 days. [11/05 Tiffany] Though this part also counts in the man day? (CP) Yes
10 | Dropbox: As we are concerned about if we save all the product photos and AIs in Dropbox (first steps is around 3000s items), will it capable to load the info on website smoothly? Do you have any experience on this part? | 1 | (CP) We can handle this by adding a field that stores the image url (from dropbox) in NetSuite and ask the website to read the image from there.
11 | Will Topline be the one owned the whole source code or Fern? If it’s owned by Fern, could we get it with a fee? If yes, what will be the range of the price? |  | (CP) The codes we developed will store with your NetSuite account and you will have the source. No extra charge applied. We will grant you the right to use it in our agreement.
12 | If we may have new website in the future, will Netsuite be able to link to two websites? Could they share same source code in Netsuite? |  | (CP) NetSuite can handle multiple websites with the same backoffice ERP. You need to pay NetSuite extra subscription cost for extra domain, though.